## Gantt Chart
DISSERTATION GANTT CHART
PROJECT TITLE | DATA VISUALIZATION FOR CYBERSECURITY METRICS AND REPORTING
|  |  |  | JULY | [14 empty] | AUGUST
TASK | MILESTONE | FUTURE TIMELINE | PROGRESS STATUS OF MILESTONE | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3
ID | TITLE |  |  | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Introduction
1.1 | Introduction | 2023-10-07 | COMPLETED | bar: WEEK 2 M
1.2 | Research Questions/ Problem Statement | 2023-10-07 | COMPLETED | bar: WEEK 2 M
1.3 | Aim | 2023-11-07 | COMPLETED | bar: WEEK 2 T
1.4 | Objectives | 2023-11-07 | COMPLETED | bar: WEEK 2 T
1.5 | Legal, Social, Ethical,and Professional Considerations | 2023-11-07 | COMPLETED | bar: WEEK 2 T
1.6 | Background | 2023-12-07 | COMPLETED | bar: WEEK 2 W
1.7 | Report Overview | 2023-12-07 | COMPLETED | bar: WEEK 2 W
2 | Literature Review/Technology Review | 17/7/2023 | ON-GOING | bar: WEEK 3 M to WEEK 3 R
3 | Methodology | bar: WEEK 3 M to WEEK 3 R
3.1 | Cyber Security Data collection and Preprocessing | 24/07/2023 | ON-GOING | bar: WEEK 3 M to WEEK 4 M
3.2 | Dashboard design Method | 24/07/2023 | NOT-STARTED | bar: WEEK 3 M to WEEK 4 M
3.3 | Project Management | 24/07/2023 | NOT-STARTED | bar: WEEK 3 M to WEEK 4 M
3.4 | Project Report Delivery Schedule | 24/07/2023 | NOT-STARTED | bar: WEEK 3 M to WEEK 4 M
3.5 | Artefact (Dashboard) Delivery Schedule | 24/07/2023 | NOT-STARTED | bar: WEEK 3 M to WEEK 4 M
4 | Implementation | 2023-01-08 | NOT-STARTED | bar: WEEK 3 M to WEEK 3 F; WEEK 1 T
5 | Results | bar: WEEK 3 M to WEEK 3 F
5.1 | Evaluation | 2023-08-08 | NOT-STARTED | bar: WEEK 3 M to WEEK 3 F; WEEK 2 M
5.2 | Related Work | 2023-08-08 | NOT-STARTED | bar: WEEK 3 M to WEEK 3 F; WEEK 2 M
6 | Conclusion | bar: WEEK 3 M to WEEK 3 F
6.1 | Reflection | 15/8/2023 | NOT-STARTED | bar: WEEK 3 M to WEEK 3 F; WEEK 3 M
6.2 | Future work | 15/8/2023 | NOT-STARTED | bar: WEEK 3 M to WEEK 3 F; WEEK 3 M
7 | References | 15/8/2023 | NOT-STARTED | bar: WEEK 3 M to WEEK 3 F; WEEK 3 M